## Month 1 — Project Plan
EISP — Month 1 Project Plan ¦ Phase 1: Identity Foundation ¦ 30 Mar – 23 Apr 2026
Week | Main Task (Monday.com) | Subtask / Activity | Day | Hours | Rubric Item | Deliverable | Status
── Week 1 Focus: Architecture foundations + Security Policy + Encryption ──
Week 1 | Project Kickoff & Architecture Review | Read EISP v1.1 design doc. Define project scope, objectives & success criteria. Note all 9 rubric items. | Mon 30 Mar | 1.5 hrs | — | Scope & objectives doc | To Do
Week 1 | Technology Stack Finalization | Confirm Entra ID vs Okta, AWS region, Terraform & Vault versions. Write tech stack decision doc with rationale. | Mon 30 Mar | 1.5 hrs | — | Tech stack decision doc | To Do
Week 1 | Network & Cloud Infrastructure Design | Design AWS VPC, subnets & IAM boundaries. Draft Zero Trust architecture diagram (draw.io / Lucidchart). | Tue 31 Mar | 2 hrs | — | Architecture diagram | To Do
Week 1 | Project Kickoff & Architecture Review | Security Policy — write 3+ security rules/guidelines, CIA Triad section, and brief IR overview stub. | Tue–Wed | 2 hrs | CB #2 — Security Policy | Security policy document | To Do
Week 1 | Project Kickoff & Architecture Review | Encryption demo — AES-256 encrypt/decrypt of sample EISP credentials using Python. Add MD5 & SHA-256 hashing. | Wed–Thu | 2 hrs | CB #3 — Encryption | Python encryption script + output doc | To Do
Week 1 | Project Kickoff & Architecture Review | Week 1 self-review: confirm architecture diagram done, tech stack doc done, CB #2 and CB #3 complete. | Thu 2 Apr | 0.5 hrs | — | Week 1 checklist signed off | To Do
── Week 2 Focus: IdP live + SSO + Cyber Threats Analysis + Legal/Ethical ──
Week 2 | Identity Provider Provisioning | Deploy Entra ID / Okta tenant (free trial). Set up admin account, base directory, and 3 test users. | Mon 6 Apr | 1.5 hrs | — | Configured IdP tenant | To Do
Week 2 | Identity Provider Provisioning | Malware analysis — upload known sample to VirusTotal / Any.Run. Document detection results, behavioural IoCs, and EISP impact. | Mon 6 Apr | 1.5 hrs | CT #1 — Cyber Threats | Malware analysis report (Task 12A) | To Do
Week 2 | SSO Protocol Configuration | Create phishing template using SET (Parrot OS / Kali Linux) targeting an Okta / Entra ID login page. Document the credential theft vector. | Tue 7 Apr | 1.5 hrs | CT #1 — Cyber Threats | Phishing template + SET docs (Task 12B) | To Do
Week 2 | SSO Protocol Configuration | Map APT29 (or chosen APT) to MITRE ATT&CK Navigator — focus on identity TTPs: credential access, lateral movement, privilege escalation. Export Navigator layer. | Tue 7 Apr | 1.5 hrs | CT #1 — Cyber Threats | ATT&CK Navigator layer (Task 12C) | To Do
Week 2 | SSO Protocol Configuration | Configure SAML 2.0, OpenID Connect, and OAuth 2.0 endpoints in IdP. Test token issuance. | Wed 8 Apr | 1.5 hrs | — | SSO configuration docs | To Do
Week 2 | Test Application SSO Integration | Legal & ethical compliance — identify GDPR + CCPA, discuss 1 ethical consideration, explain how EISP upholds these. Add section to security policy. | Wed 8 Apr | 1 hr | CB #4 — Legal & Ethical | Legal & ethical compliance section | To Do
Week 2 | Test Application SSO Integration | Integrate test app with SSO. Complete end-to-end login flow. Screenshot successful authentication. Write SSO test report. | Thu 9 Apr | 2 hrs | — | SSO test report + integrated app | To Do
Week 2 | Test Application SSO Integration | Week 2 self-review: CT #1 complete (12A+12B+12C), CB #4 complete. IdP live and SSO working. 4 of 9 rubric items done. | Thu 9 Apr | 0.5 hrs | — | Week 2 checklist signed off | To Do
── Week 3 Focus: RBAC + Vulnerability Assessment + OpenCTI Threat Intelligence ──
Week 3 | RBAC Model Design | Define role taxonomy: Admin, Developer, Data Analyst, Security Ops, Read-Only. Map roles to AWS services and app access. Produce RBAC matrix. | Mon 13 Apr | 1.5 hrs | — | RBAC design matrix | To Do
Week 3 | RBAC Model Design | Vulnerability scan — run Nmap -sV -sC against EISP lab environment. Classify findings by CVSS severity. | Mon 13 Apr | 1 hr | CT #2 — Vulnerability Assessment | Nmap scan output + CVSS classification (Task 12D) | To Do
Week 3 | RBAC Model Design | Asset discovery scan — run Nmap -sn for host discovery. Enumerate live systems, services, and critical assets. Produce basic network map. | Mon 13 Apr | 0.5 hrs | CT #2 — Vulnerability Assessment | Asset inventory + network map (Task 12E) | To Do
Week 3 | RBAC Policy Implementation in IdP | Write up full vulnerability assessment report: methodology, findings table, CVSS scores, asset inventory, network map. Mark CT #2 complete. | Tue 14 Apr | 1 hr | CT #2 — Vulnerability Assessment | Vulnerability assessment report | To Do
Week 3 | RBAC Policy Implementation in IdP | Deploy OpenCTI via Docker (docker-compose). Configure admin credentials. Screenshot running dashboard. | Tue 14 Apr | 1 hr | CT #3 — Threat Intelligence | OpenCTI running instance (Task 12G) | To Do
Week 3 | RBAC Policy Implementation in IdP | Configure MITRE ATT&CK connector in OpenCTI. Verify TTPs ingested. Then configure AlienVault OTX connector. Screenshot both active. | Tue 14 Apr | 1 hr | CT #3 — Threat Intelligence | 2 connectors active (Task 12G) | To Do
Week 3 | RBAC Policy Implementation in IdP | Analyse 2 IoCs in OpenCTI (e.g. known phishing domain IP + malicious file hash). Document: what each IoC is, detection method, and threat indication. | Wed 15 Apr | 1 hr | CT #3 — Threat Intelligence | IoC analysis report (Task 12F) | To Do
Week 3 | RBAC Policy Implementation in IdP | Create groups, roles & permission sets in Entra ID / Okta matching the RBAC matrix. Assign test users to roles. | Wed 15 Apr | 1 hr | — | RBAC policies in IdP | To Do
Week 3 | Least Privilege Access Validation | Create matching AWS IAM roles (Developer, Analyst, Security Admin) in Terraform. Apply and confirm in AWS console. | Wed 15 Apr | 1 hr | — | AWS IAM roles (Terraform) | To Do
Week 3 | Least Privilege Access Validation | Audit all role assignments. Verify no over-provisioned accounts. Test Developer cannot access IAM. Write access audit report. | Thu 16 Apr | 1.5 hrs | — | Access audit report | To Do
Week 3 | Least Privilege Access Validation | Week 3 self-review: CT #2 complete, CT #3 complete. RBAC live in IdP and AWS. 7 of 9 rubric items done. | Thu 16 Apr | 0.5 hrs | — | Week 3 checklist signed off | To Do
── Week 4 Focus: AWS IAM + Risk Management + IR Plan + Security Monitoring — All 9 rubric items complete ──
Week 4 | AWS IAM Policy Configuration | Write Terraform HCL for AWS IAM roles, policies & permission boundaries. Run terraform apply. Confirm roles in AWS console. | Mon 20 Apr | 2 hrs | — | AWS IAM policies (Terraform code) | To Do
Week 4 | AWS IAM Policy Configuration | Risk register — from Week 3 scan: identify 2 critical CVSS findings. For each: risk description, likelihood, impact, treatment, mitigation steps. | Mon 20 Apr | 1 hr | CT #4 — Risk Management | Risk register table (Task 12H) | To Do
Week 4 | AWS IAM & IdP Federation | Risk monitoring SOP — 1-page procedure: who reviews the risk register, how often, what triggers re-assessment, how remediation is logged. Mark CT #4 complete. | Tue 21 Apr | 1 hr | CT #4 — Risk Management | Risk monitoring SOP | To Do
Week 4 | AWS IAM & IdP Federation | Security monitoring use case — configure failed MFA spike detection rule (5 failures / 10 min). Document rule logic, alert priority, and response procedure. | Tue 21 Apr | 1 hr | CT #5 — Security Monitoring & IR | Detection rule + use case doc (Task 12I) | To Do
Week 4 | AWS IAM & IdP Federation | IR scenario for credential theft — classification, detection trigger, containment (disable account, revoke tokens), eradication, recovery, lessons learned. | Tue 21 Apr | 1 hr | CT #5 — Security Monitoring & IR | IR scenario document (Task 12J) | To Do
Week 4 | AWS IAM & IdP Federation | Configure SAML federation between Entra ID / Okta and AWS. Test cross-platform role assumption with test user. Document configuration. | Wed 22 Apr | 1.5 hrs | — | Federation test results | To Do
Week 4 | Phase 1 Review & Sign-Off | Full IR plan (CB #1) — compile: 1 detection method, 1 containment strategy, eradication + recovery steps, explanation of Phishing as attack type. Mark CB #1 complete. | Wed 22 Apr | 1.5 hrs | CB #1 — Incident Response Plan | Full IR plan document | To Do
Week 4 | Phase 1 Review & Sign-Off | Confirm all 9 rubric deliverables exist. Compile rubric evidence folder (one doc per rubric item). | Thu 23 Apr | 1.5 hrs | All 9 items | Rubric evidence folder | To Do
Week 4 | Phase 1 Review & Sign-Off | Phase 1 review: check all Tasks 1–11 deliverables. Note any gaps. Write Month 1 lessons learned. Preview Phase 2 scope. | Thu 23 Apr | 1.5 hrs | — | Phase 1 completion report | To Do

## Rubric Tracker
EISP — Month 1 Rubric Tracker ¦ 9 Items ¦ Target: All Complete by 23 Apr 2026
# | Course | Rubric Item | What it requires | EISP deliverable that covers it | Planned week | Status
CB #1 | Cybersecurity Basics | Create an Incident Response Plan | 1 detection method, 1 containment strategy, eradication & recovery steps, explain 1 attack type (Malware/Phishing/Ransomware/DoS) | Full IR plan doc built in Week 4. Detection = MFA spike rule. Containment = account lockout. Attack type = Phishing (links to Week 2 SET template). | Week 4 | To Do
CB #2 | Cybersecurity Basics | Develop a Comprehensive Security Policy | 3+ security rules/guidelines, incident response overview, CIA Triad section | Security policy document started Week 1. Covers: password policy, access control rule, data classification, IR overview stub, CIA Triad alignment. | Week 1 | To Do
CB #3 | Cybersecurity Basics | Apply Encryption Techniques | Show AES encrypted + decrypted text, and a SHA or MD5 hash | Python script (Week 1): AES-256 encrypt/decrypt of sample EISP credentials. SHA-256 and MD5 hash outputs. Method explanation doc. | Week 1 | To Do
CB #4 | Cybersecurity Basics | Demonstrate Legal & Ethical Compliance | 2 relevant laws/regulations, 1 ethical consideration, explain how plan upholds them | Legal & ethical section added to security policy (Week 2). Laws: GDPR + CCPA. Ethical consideration: employee monitoring. EISP access policy alignment explained. | Week 2 | To Do
CT #1 | Cyber Threats & Vulnerabilities | Identify and Analyze Cyber Threats | Malware sample analysis (VirusTotal / Any.Run), 1 phishing template (SET), 1 APT mapped to MITRE ATT&CK | Week 2: Task 12A = malware report. Task 12B = SET phishing template targeting Entra ID / Okta login. Task 12C = APT29 ATT&CK Navigator layer. | Week 2 | To Do
CT #2 | Cyber Threats & Vulnerabilities | Apply Vulnerability Assessment Techniques | 1 vulnerability scan (Nmap / OpenVAS) with findings & classification, 1 asset discovery scan with network map | Week 3: Task 12D = Nmap -sV -sC scan of EISP lab with CVSS classification. Task 12E = host discovery scan, asset inventory table, basic network map. | Week 3 | To Do
CT #3 | Cyber Threats & Vulnerabilities | Implement Threat Intelligence Principles | OpenCTI deployed (Docker), 2 connectors configured, 2 IoCs analysed with detection methods | Week 3: Task 12G = OpenCTI via Docker, MITRE ATT&CK connector + AlienVault OTX connector. Task 12F = 2 IoC analyses (phishing domain + malicious hash). | Week 3 | To Do
CT #4 | Cyber Threats & Vulnerabilities | Develop and Apply Risk Management Strategies | 2 critical risks from scan, treatment recommendations, mitigation steps, 1 risk monitoring procedure | Week 4: Task 12H = risk register with 2 critical findings from Week 3 Nmap scan. Risk monitoring SOP with review cadence. | Week 4 | To Do
CT #5 | Cyber Threats & Vulnerabilities | Implement Security Monitoring & Incident Response | 1 monitoring use case with detection rule & alert prioritization, 1 IR scenario (classification, response steps, lessons learned) | Week 4: Task 12I = failed MFA spike detection rule. Task 12J = credential theft IR scenario with full playbook. | Week 4 | To Do

## Weekly Milestones
EISP — Month 1 Weekly Milestones & Rubric Progress
Week | Dates | Project milestone | Rubric items completing this week | Cumulative rubric count | % complete
Week 1 | 30 Mar – 2 Apr | EISP architecture diagram done. Tech stack finalised. AWS VPC design complete. | CB #2 — Security Policy CB #3 — Encryption | 2 of 9 | 22.22%
Week 2 | 6 Apr – 9 Apr | IdP tenant live. SAML / OIDC / OAuth configured. SSO test app integrated and validated. | CT #1 — Cyber Threats Analysis (malware + phishing + ATT&CK) CB #4 — Legal & Ethical Compliance | 4 of 9 | 44.44%
Week 3 | 13 Apr – 16 Apr | RBAC live in IdP and AWS. Least privilege audit passed. Vulnerability scan done. OpenCTI running with 2 connectors. | CT #2 — Vulnerability Assessment CT #3 — Threat Intelligence (OpenCTI + IoCs) | 7 of 9 | 77.78%
Week 4 | 20 Apr – 23 Apr | AWS IAM + IdP federation working. Phase 1 signed off. All 9 rubric items complete and evidenced. | CT #4 — Risk Management CT #5 — Security Monitoring & IR CB #1 — Incident Response Plan | 9 of 9 | 100%