## EISP Project Plan
Enterprise Identity Security Platform (EISP) — 12-Week Project Plan
Start: 30 March 2026 ¦ End: 25 June 2026 ¦ Working Days: Monday–Thursday ¦ Author: Manisha Gupta
# | Week | Task Name | Task Description | Start Date | End Date | Duration (Days) | Complexity | Owner / Role | Dependencies | Deliverable | Status
PHASE 1 — IDENTITY FOUNDATION
WEEK 1 — 30 Mar 2026 to 02 Apr 2026
1 | Week 1 | Project Kickoff & Architecture Review | Define project scope, objectives, and success criteria. Review EISP design document and align stakeholders. | 30 Mar 2026 | 31 Mar 2026 | 2 | Easy | Project Manager | — | Kickoff deck, scope document | Not Started
PHASE 1 — IDENTITY FOUNDATION
2 | Week 1 | Technology Stack Finalization | Confirm selection of Microsoft Entra ID / Okta, Terraform, HashiCorp Vault, and AWS. Document tool versions. | 30 Mar 2026 | 30 Mar 2026 | 1 | Medium | Architect / Tech Lead | Task 1 | Tech stack decision document | Not Started
PHASE 1 — IDENTITY FOUNDATION
3 | Week 1 | Network & Cloud Infrastructure Design | Design AWS VPC, subnets, IAM policies. Draft high-level Zero Trust architecture diagram. | 30 Mar 2026 | 30 Mar 2026 | 1 | Difficult | Cloud Architect | Task 2 | Architecture diagram, AWS design doc | Not Started
WEEK 2 — 06 Apr 2026 to 09 Apr 2026
4 | Week 2 | Identity Provider Provisioning | Deploy and configure Microsoft Entra ID or Okta tenant. Set up admin accounts and base directory structure. | 06 Apr 2026 | 07 Apr 2026 | 2 | Medium | IAM Engineer | Week 1 tasks | Configured IdP tenant | Not Started
5 | Week 2 | SSO Protocol Configuration (SAML/OIDC) | Configure SAML 2.0 and OpenID Connect endpoints. Set up OAuth 2.0 authorization flows. | 06 Apr 2026 | 06 Apr 2026 | 1 | Difficult | IAM Engineer | Task 4 | SSO configuration documentation | Not Started
6 | Week 2 | Test Application SSO Integration | Integrate one internal test application with SSO. Validate login flows and token handling. | 06 Apr 2026 | 06 Apr 2026 | 1 | Medium | IAM Engineer / QA | Task 5 | SSO test report, integrated app | Not Started
WEEK 3 — 13 Apr 2026 to 16 Apr 2026
7 | Week 3 | RBAC Model Design | Define role taxonomy: Admin, Developer, Analyst, Read-Only, Security Ops. Map roles to job functions. | 13 Apr 2026 | 14 Apr 2026 | 2 | Medium | IAM Architect | Week 2 tasks | RBAC design matrix | Not Started
8 | Week 3 | RBAC Policy Implementation in IdP | Create groups, roles, and permission sets in Entra ID / Okta. Assign test users to roles. | 13 Apr 2026 | 13 Apr 2026 | 1 | Medium | IAM Engineer | Task 7 | RBAC policies in IdP | Not Started
9 | Week 3 | Least Privilege Access Validation | Audit role assignments. Verify no over-provisioned accounts. Test privilege boundaries. | 13 Apr 2026 | 13 Apr 2026 | 1 | Difficult | Security Analyst | Task 8 | Access audit report | Not Started
WEEK 4 — 20 Apr 2026 to 23 Apr 2026
10 | Week 4 | AWS IAM Policy Configuration | Create AWS IAM roles, policies, and permission boundaries. Align with Zero Trust principles. | 20 Apr 2026 | 21 Apr 2026 | 2 | Difficult | Cloud/IAM Engineer | Week 3 tasks | AWS IAM policies (Terraform) | Not Started
11 | Week 4 | AWS IAM & IdP Federation | Configure identity federation between Entra ID/Okta and AWS. Test cross-platform role assumption. | 20 Apr 2026 | 20 Apr 2026 | 1 | Difficult | Cloud/IAM Engineer | Task 10 | Federation test results | Not Started
12 | Week 4 | Phase 1 Review & Sign-Off | Review all Phase 1 deliverables. Document issues, gaps. Obtain stakeholder sign-off. | 20 Apr 2026 | 20 Apr 2026 | 1 | Easy | Project Manager | Tasks 1–11 | Phase 1 completion report | Not Started
PHASE 2 — IDENTITY GOVERNANCE
WEEK 5 — 27 Apr 2026 to 30 Apr 2026
13 | Week 5 | HR Data Source Integration | Connect HR system (e.g., Workday/mock) to IdP via SCIM. Map employee attributes to identity fields. | 27 Apr 2026 | 28 Apr 2026 | 2 | Difficult | IAM Engineer | Week 4 tasks | SCIM integration setup | Not Started
PHASE 2 — IDENTITY GOVERNANCE
14 | Week 5 | Joiner Automation Script (Python) | Build Python automation for new employee onboarding: create account, assign role, send welcome email. | 27 Apr 2026 | 28 Apr 2026 | 2 | Medium | Python Developer | Task 13 | Joiner automation script | Not Started
WEEK 6 — 04 May 2026 to 07 May 2026
15 | Week 6 | Mover Automation Script (Role Change) | Implement automated role reassignment when employee changes department. Test with mock HR events. | 04 May 2026 | 05 May 2026 | 2 | Medium | Python Developer | Task 14 | Mover automation script | Not Started
16 | Week 6 | Leaver Automation Script (Offboarding) | Build termination automation: disable account, revoke tokens, archive user data, notify security team. | 04 May 2026 | 05 May 2026 | 2 | Difficult | Python Developer | Task 15 | Leaver automation script | Not Started
WEEK 7 — 11 May 2026 to 14 May 2026
17 | Week 7 | HashiCorp Vault Deployment | Deploy HashiCorp Vault on AWS. Configure storage backend, TLS, and Vault auto-unseal mechanism. | 11 May 2026 | 12 May 2026 | 2 | Difficult | DevSecOps Engineer | Week 6 tasks | Running Vault instance on AWS | Not Started
18 | Week 7 | Vault Secret Engines Configuration | Enable KV, AWS, and database secret engines. Create policies and AppRole authentication method. | 11 May 2026 | 12 May 2026 | 2 | Difficult | DevSecOps Engineer | Task 17 | Vault policies and secret engines | Not Started
WEEK 8 — 18 May 2026 to 21 May 2026
19 | Week 8 | Automatic Credential Rotation Setup | Configure Vault to auto-rotate AWS keys and database passwords on schedule. Set TTL and lease policies. | 18 May 2026 | 19 May 2026 | 2 | Difficult | DevSecOps Engineer | Task 18 | Credential rotation config & tests | Not Started
20 | Week 8 | Dynamic Secret Generation Integration | Integrate dynamic secret generation for app services. Validate ephemeral credentials across test apps. | 18 May 2026 | 18 May 2026 | 1 | Difficult | DevSecOps Engineer / Dev | Task 19 | Dynamic secrets integration report | Not Started
21 | Week 8 | Phase 2 Review & Sign-Off | Review Phase 2 deliverables. Validate automation scripts and secrets management. Stakeholder sign-off. | 18 May 2026 | 18 May 2026 | 1 | Easy | Project Manager | Tasks 13–20 | Phase 2 completion report | Not Started
PHASE 3 — IDENTITY SECURITY
WEEK 9 — 25 May 2026 to 28 May 2026
22 | Week 9 | Identity Log Pipeline Setup | Configure centralized log collection from Entra ID / Okta and AWS. Route logs to SIEM (Sentinel/Splunk). | 25 May 2026 | 26 May 2026 | 2 | Difficult | Security Engineer | Week 8 tasks | Log pipeline architecture & config | Not Started
PHASE 3 — IDENTITY SECURITY
23 | Week 9 | Microsoft Defender for Identity Deployment | Deploy and configure Microsoft Defender for Identity. Connect to Entra ID for real-time signal collection. | 25 May 2026 | 26 May 2026 | 2 | Difficult | Security Engineer | Task 22 | Defender deployment report | Not Started
WEEK 10 — 01 Jun 2026 to 04 Jun 2026
24 | Week 10 | Threat Detection Rules — Brute Force & Credential Theft | Write detection rules for brute-force login attempts and credential stuffing. Test with simulated attacks. | 01 Jun 2026 | 02 Jun 2026 | 2 | Difficult | Security Analyst | Task 23 | Detection rules documentation | Not Started
25 | Week 10 | Threat Detection Rules — Privilege Escalation & Anomalies | Define rules for unusual privilege escalation patterns and impossible travel anomalies. | 01 Jun 2026 | 02 Jun 2026 | 2 | Difficult | Security Analyst | Task 24 | Updated detection rule set | Not Started
WEEK 11 — 08 Jun 2026 to 11 Jun 2026
26 | Week 11 | Automated Response Playbook — Account Disable | Implement automated playbook to disable accounts upon high-severity alerts. Test end-to-end trigger. | 08 Jun 2026 | 09 Jun 2026 | 2 | Difficult | Security Engineer | Week 10 tasks | Auto-response playbook (code + docs) | Not Started
27 | Week 11 | Automated Response Playbook — Alert & Notify | Configure automated notifications (email/Slack) to security team upon identity threat detection. | 08 Jun 2026 | 09 Jun 2026 | 2 | Medium | Security Engineer | Task 26 | Notification playbook & test results | Not Started
WEEK 12 — 15 Jun 2026 to 18 Jun 2026
28 | Week 12 | End-to-End System Testing | Execute full system test: identity lifecycle, SSO, RBAC, secrets, and threat detection scenarios. | 15 Jun 2026 | 16 Jun 2026 | 2 | Difficult | QA / Security Team | Week 11 tasks | System test report | Not Started
29 | Week 12 | Security Audit & Compliance Review | Review all configurations against Zero Trust and least-privilege standards. Remediate findings. | 15 Jun 2026 | 15 Jun 2026 | 1 | Difficult | Security Architect | Task 28 | Audit report with findings | Not Started
30 | Week 12 | Final Documentation & Project Close | Produce final architecture docs, runbooks, and lessons learned. Present to stakeholders. Close project. | 15 Jun 2026 | 15 Jun 2026 | 1 | Easy | Project Manager | Tasks 1–29 | Final documentation bundle | Not Started
COMPLEXITY LEGEND
Easy |  | Low complexity. Well-defined steps, minimal risk, straightforward execution.
Medium |  | Moderate complexity. Requires coordination, technical skill, or integration work.
Difficult |  | High complexity. Multi-system integration, security-critical, or advanced engineering required.