RISK MITIGATION PLANNING

Enterprise Identity Security Platform (EISP)

Document ID: RSK-EISP-04

Version: 1.0

Date: October 2026

Prepared by: Manisha Gupta

Classification: Internal

Source register: EISP-RR-003 (EISP Risk Register)

# 1. Executive Summary

This document presents the risk mitigation plan for the Enterprise Identity Security Platform (EISP) — the Authentik-based identity provider and Terraform-managed AWS IAM environment built as an IAM-engineer hands-on project. It operationalizes the risks recorded in the EISP Risk Register (EISP-RR-003) by selecting controls from two industry frameworks — NIST Cybersecurity Framework (CSF) 2.0 and ISO/IEC 27001:2022 Annex A — applying all four risk treatment strategies (mitigate, avoid, transfer, accept), and calculating residual risk after control implementation.

Six risks rated HIGH or CRITICAL drive this plan: credential theft (RR-001), privilege escalation (RR-002), hardcoded secrets exposure (RR-003), MFA fatigue attacks (RR-004), Vault token compromise (RR-005), and detection-rule gaps (RR-010). Three of these are directly evidenced in the project's own configuration files (a hardcoded LDAP service token and AUTHENTIK_INSECURE=true in docker-compose.yml; the worker container running as root with the Docker socket mounted), which makes mitigation concrete rather than theoretical.

Key outcomes of this plan:

- 18 framework controls selected (NIST CSF 2.0 + ISO 27001:2022), each with rationale and cost-benefit analysis.

- A prioritized 6-month mitigation roadmap split into quick wins (0–30 days) and strategic initiatives (1–6 months).

- Residual risk recalculated for every top risk; all CRITICAL inherent risks are reduced to MEDIUM or lower.

- Control effectiveness metrics and monitoring procedures aligned to the register's Monitoring SOP, so mitigation stays verifiable over time.

# 2. Control Selection Using Industry Frameworks

## 2.1 Selection Methodology

Controls were selected in four steps:

- Step 1 — Map each top risk to the attack technique or weakness it represents (MITRE ATT&CK IDs are taken from EISP-RR-003).

- Step 2 — Identify candidate controls in NIST CSF 2.0 (Govern, Identify, Protect, Detect, Respond, Recover) and ISO/IEC 27001:2022 Annex A that directly address the technique.

- Step 3 — Score each candidate on relevance, coverage overlap with controls already present in EISP (e.g., the Terraform permission boundary), and implementation cost.

- Step 4 — Record rationale and cost-benefit; prefer controls that are native to Authentik/AWS/Terraform (low cost, high leverage) before buying new tooling.

All cost figures below are illustrative estimates for a lab/small-team deployment, not vendor quotes.

## 2.2 NIST Cybersecurity Framework 2.0 — Selected Controls

| Risk ID | NIST CSF 2.0 Control | Control Name | Detailed Rationale |
| --- | --- | --- | --- |
| RR-001 | PR.AC-07 | Multi-factor authentication is implemented | Directly counters credential theft (T1566/T1110): even with a stolen password, the attacker cannot complete Authentik authentication. Authentik supports WebAuthn/TOTP natively, so this is a configuration change, not a purchase. |
| RR-001 | DE.CM-01 | Networks, platforms, and services are monitored | Impossible-travel and failed-login monitoring in Wazuh/Authentik event logs detects stolen-credential use. Complements PR.AC-07 with detection when prevention is bypassed. |
| RR-002 | PR.AC-04 | Access permissions are managed with least privilege | The Terraform EISP-PermissionBoundary already implements this; the control formalizes keeping it attached to every role and reviewing the three RBAC policies (Developer, SecurityAnalyst, IAMEngineer) quarterly. |
| RR-002 | PR.AC-01 | Identities and credentials are managed for authorized users, services, and hardware | Covers the SAML federation trust (authentik-saml with SAML:aud condition) and 4-hour STS session limits already in main.tf — ensures federated identities cannot exceed intended scope. |
| RR-003 | PR.DS-01 | Confidentiality of data-at-rest is protected | Secrets (LDAP token, DB passwords, Authentik secret key) must not live in plaintext compose files or git history; requires migration to a secrets manager (Vault) and encrypted .env handling. |
| RR-003 | PR.PS-01 | Policy-driven configuration of platforms is maintained | docker-compose.yml is infrastructure-as-code and must be scanned (pre-commit hooks, Trufflehog) so hardcoded secrets like AUTHENTIK_TOKEN cannot be reintroduced. |
| RR-004 | PR.AC-07 | Multi-factor authentication (number matching, rate limits) | Number-matching MFA plus push rate-limiting (max 3 per 5 minutes) defeats fatigue attacks (T1621) where users approve out of frustration. |
| RR-005 | PR.AC-04 / PR.DS-01 | Least privilege + secret confidentiality for Vault | Root token revoked after bootstrap; AppRole secret_id TTL 24h with use-limit 5; Vault audit logging enabled — bounds the blast radius of any single token. |
| RR-010 | DE.CM-01 / DE.CM-03 | Monitoring for adverse events; personnel activity monitored | Closes detection gaps (T1562.001): the six mandatory Wazuh rules (MFA spikes, self-policy modification, impossible travel) must exist, be tested with simulated events, and be reviewed monthly. |
| RR-001–005 | GV.OC-01 | Organizational mission and stakeholders understood | Governance control: assigns the IAM Engineer / DevSecOps owners from the risk register and defines escalation to the Security Lead, so every technical control has an accountable owner. |

## 2.3 ISO/IEC 27001:2022 Annex A — Selected Controls

| Risk ID | ISO 27001:2022 Control | Control Name | Detailed Rationale |
| --- | --- | --- | --- |
| RR-001 | A.8.5 | Secure authentication | Normative basis for MFA enforcement in Authentik and account lockout after 5 failed attempts — the primary RR-001 mitigations. |
| RR-001 | A.5.17 | Authentication information | Requires secure allocation, storage, and rotation of authentication secrets; underpins the 'rotate all credentials on suspected compromise' procedure. |
| RR-002 | A.5.18 | Access rights | Requires provisioning, review, and removal of access rights per least privilege — implemented via the Terraform RBAC roles plus quarterly recertification. |
| RR-002 | A.5.15 | Access control | Policy-level requirement that access to EISP (Authentik admin, AWS console, LDAP) follows the documented access-control policy, including the us-east-1-only permission boundary. |
| RR-003 | A.8.9 | Configuration management | Hardcoded AUTHENTIK_TOKEN violates secure configuration; requires secrets moved out of compose files into Vault and config baselines versioned in git. |
| RR-004 | A.8.5 | Secure authentication | Number-matching and push rate limits are the ISO-recognized hardening of MFA against fatigue/social-engineering bypass. |
| RR-004 | A.6.3 | Information security awareness, education and training | Users must be trained never to approve unexpected MFA prompts and to report them — the human layer of the RR-004 mitigation. |
| RR-005 | A.8.15 | Logging | Vault audit logging (who accessed which secret path, when) is required to detect token misuse; feeds the weekly Vault audit-log review in the Monitoring SOP. |
| RR-010 | A.8.16 | Monitoring activities | Requires networks/systems/applications to be monitored for anomalies — the basis for the Wazuh detection-rule program and monthly coverage reviews. |
| RR-001–010 | A.5.24 | Incident management planning and preparation | Ensures the incident response procedures referenced by RR-001/RR-002 mitigations (credential rotation, containment) are documented, assigned, and tested. |

## 2.4 Cost-Benefit Analysis

Costs are illustrative estimates for a lab/small-team deployment.

| Control (framework) | Risk(s) | Illustrative Cost / Effort | Expected Risk Reduction | Priority |
| --- | --- | --- | --- | --- |
| Enforce MFA + number matching (PR.AC-07 / A.8.5) | RR-001, RR-004 | Low — Authentik native; ~4 hours config + user enrollment | CRITICAL→MEDIUM; HIGH→MEDIUM | P1 |
| Rotate hardcoded LDAP token into Vault; set AUTHENTIK_INSECURE=false with LDAPS (PR.DS-01 / A.8.9) | RR-003 | Low–Medium — ~1 day incl. testing; Vault already in scope | HIGH→LOW | P1 |
| Pre-commit secret scanning: git-secrets + Trufflehog (PR.PS-01 / A.8.9) | RR-003 | Low — free tooling; ~2 hours setup | Prevents recurrence; HIGH→LOW combined | P1 |
| Revoke Vault root token; AppRole TTL 24h + use-limit (PR.DS-01 / A.5.17) | RR-005 | Low — ~2 hours | HIGH→LOW | P1 |
| Wazuh detection rules: MFA spike, self-policy mod, impossible travel (DE.CM / A.8.16) | RR-001, RR-002, RR-004, RR-010 | Medium — ~3 days to write, test with simulated events | Closes HIGH detection gap; enables weekly reviews | P1 |
| Quarterly access recertification incl. permission boundary check (PR.AC-04 / A.5.18) | RR-002 | Low — ~4 hours/quarter (recurring) | CRITICAL→MEDIUM sustained | P2 |
| Run worker as non-root; remove docker.sock mount or scope it (PR.PS-01 / A.8.9) | RR-002 | Low–Medium — ~half day + regression test | Reduces container-escape blast radius | P2 |
| User awareness: MFA-prompt phishing reporting (PR.AT / A.6.3) | RR-001, RR-004 | Low — 1-hour session + one-pager | Reduces human-factor bypass | P2 |
| Remove whoami test app from production profile (Avoid — PR.PS-01) | Attack surface | Negligible — compose profile change | Eliminates an unnecessary exposed service | P2 |
| Cyber insurance (Transfer) | Residual breach liability | Illustrative ~$2k–$5k/yr for small org | Financial transfer, not risk reduction | P3 |

Rationale summary: the highest-ROI controls are all configuration changes in systems EISP already runs (Authentik, Terraform, Wazuh, Vault) — no new product purchases are required to move every CRITICAL risk down to MEDIUM or lower. Insurance (transfer) is deliberately ranked P3: it caps financial loss but does not reduce the likelihood or technical impact of an incident.

# 3. Risk Treatment Options

Each top risk is assigned one of the four standard treatment strategies. The decision logic: treat risks with feasible, cost-effective controls via mitigation; eliminate risk sources that serve no business purpose via avoidance; shift financial consequences that cannot be engineered away via transfer; and formally accept only residual risks whose impact is tolerable and whose acceptance is signed off.

## 3.1 Mitigate — Reduce Likelihood and/or Impact

Mitigation is the primary strategy for all CRITICAL and HIGH risks, using the controls selected in Section 2.

| Risk | Mitigation Actions | Timeline | Resource Requirements |
| --- | --- | --- | --- |
| RR-001 Credential Theft (CRITICAL) | 1. Enforce MFA (WebAuthn/TOTP) for all Authentik users. 2. Account lockout after 5 failed attempts. 3. Wazuh impossible-travel + failed-login rules; daily sign-in log review. | Weeks 1–2: MFA enforcement + lockout. Weeks 3–4: detection rules live. | IAM Engineer (~3 days); Wazuh already deployed; no license cost. |
| RR-002 Privilege Escalation (CRITICAL) | 1. Keep EISP-PermissionBoundary attached to all roles (already in Terraform). 2. Wazuh alert on AttachRolePolicy/CreateRole outside change log. 3. JIT elevation for privileged roles (4h STS sessions already configured). | Week 2: detection rule. Month 2: JIT workflow documented. | IAM Engineer (~2 days); Security Analyst for rule testing. |
| RR-003 Hardcoded Secrets (HIGH) | 1. Rotate the hardcoded AUTHENTIK_TOKEN immediately; store in Vault. 2. Set AUTHENTIK_INSECURE=false and terminate LDAP with TLS (LDAPS on 636). 3. Install git-secrets pre-commit hooks; Trufflehog scan of repo history. | Days 1–3: rotation + LDAPS. Week 2: scanning in CI. | DevSecOps Engineer (~2 days); Vault in scope. |
| RR-004 MFA Fatigue (HIGH) | 1. Enable number matching on push MFA. 2. Rate limit: max 3 pushes per 5 minutes. 3. Wazuh MFA-spike detection; user reporting training. | Week 3: Authentik policy change. Month 2: training session. | IAM Engineer (~1 day); 1-hour user training. |
| RR-005 Vault Token Compromise (HIGH) | 1. Revoke Vault root token after bootstrap. 2. AppRole secret_id TTL 24h, use-limit 5. 3. Weekly Vault audit-log review. | Week 1: token hygiene. Ongoing: weekly reviews. | DevSecOps Engineer (~1 day). |
| RR-010 Detection Gaps (HIGH) | 1. Implement the 6 mandatory Wazuh rules. 2. Test each with a simulated event before sign-off. 3. Monthly rule-coverage review. | Month 1: rules live + tested. Ongoing: monthly reviews. | Security Analyst (~3 days). |

## 3.2 Avoid — Eliminate the Risk Source

Avoidance is used where a risk source provides no production value and can simply be removed.

| Avoidance Action | Risk Eliminated | Timeline | Resource Requirements |
| --- | --- | --- | --- |
| Remove the whoami test application from the production Docker Compose profile (keep it in a dev-only profile). | Unnecessary exposed HTTP service that expands the attack surface and could leak deployment details. | Day 1 — single compose-file change. | IAM Engineer (~30 minutes); regression test of remaining services. |
| Bind the LDAP outpost to the internal Docker network only; do not publish port 389/636 to the host unless a specific consumer requires it. | Internet-adjacent cleartext LDAP exposure (compounded by AUTHENTIK_INSECURE=true). | Week 1 — compose network change + consumer verification. | DevSecOps Engineer (~2 hours). |

## 3.3 Transfer — Shift Financial Consequences

Transfer does not reduce the probability of an incident; it caps the financial impact to the organization.

| Transfer Mechanism | What Is Transferred | Timeline | Resource Requirements |
| --- | --- | --- | --- |
| Cyber insurance policy (illustrative small-organization policy). | Breach response costs: forensics, notification, legal, and third-party liability arising from an identity-platform compromise. | Month 2–3: broker engagement, application, underwriting. | Illustrative ~$2k–$5k/year premium; requires completed MFA + logging controls for insurability (underwriters ask). |
| Cloud shared-responsibility model (AWS). | Physical security, hypervisor patching, and facility resilience for the AWS-hosted components — contractually with the provider via SLA. | Already in effect via AWS account. | None incremental; verify SLA terms annually. |

Note: transfer is complementary to mitigation, never a substitute — an insurer will not pay out if gross negligence (e.g., no MFA, hardcoded secrets) caused the loss.

## 3.4 Accept — Formally Acknowledge Residual Risk

Acceptance is documented, time-bound, and signed — never implicit.

| Accepted Risk | Justification | Conditions & Review | Sign-off |
| --- | --- | --- | --- |
| Residual risk of single-host Docker deployment for the lab (availability; no HA). | Lab/educational scope; cost of multi-AZ HA outweighs the availability impact for a non-production identity lab. | Accepted until next semester review or any production use — whichever comes first. Revisit if EISP moves toward production. | System Owner signature + date. |
| RR-006 OpenCTI resource exhaustion (MEDIUM) — partial acceptance with mitigation. | Peripheral to the IAM mission; Docker Desktop resource allocation is the practical control. | Monitor Docker RAM at each deployment (per the Monitoring SOP); escalate if utilization exceeds 90%. | DevSecOps Engineer sign-off. |

A risk acceptance record captures: risk ID, description, residual score, justification, expiry/review date, and approver signature. Accepted risks remain on the register and are re-evaluated at each review cycle.

## 3.5 Treatment Decision Summary

| Risk ID | Risk | Inherent Rating | Treatment | Primary Owner |
| --- | --- | --- | --- | --- |
| RR-001 | Credential Theft | CRITICAL | Mitigate | IAM Engineer |
| RR-002 | Privilege Escalation | CRITICAL | Mitigate | IAM Engineer |
| RR-003 | Secrets Exposure (hardcoded) | HIGH | Mitigate | DevSecOps Engineer |
| RR-004 | MFA Fatigue | HIGH | Mitigate | IAM Engineer |
| RR-005 | Vault Token Compromise | HIGH | Mitigate | DevSecOps Engineer |
| RR-010 | Detection Rule Gaps | HIGH | Mitigate | Security Analyst |
| — | whoami test app exposure | MEDIUM | Avoid | IAM Engineer |
| — | Breach financial liability | — | Transfer (insurance) | System Owner |
| — | Single-host lab availability | MEDIUM | Accept (time-bound) | System Owner |

# 4. Comprehensive Mitigation Strategy

## 4.1 Strategy Statement

EISP's mitigation strategy is: "Harden the identity plane first, because every other system's security depends on it — using native Authentik, AWS, and Terraform controls before any new spending, with detection and formal acceptance closing the remaining gaps." This aligns to the business objectives below.

| Business Objective | How Mitigation Serves It |
| --- | --- |
| Demonstrate production-grade IAM engineering skills | MFA, RBAC, permission boundaries, and audited procedures are exactly what hiring managers assess. |
| Keep the lab operable and low-cost | All P1 controls are configuration changes (~2–3 weeks total effort); no new licenses. |
| Produce auditable evidence for the cohort | Every mitigation generates an artifact (policy export, scan report, signed acceptance) suitable for assessment. |
| Prepare EISP for production-like rigor | LDAPS, secret hygiene, and detection rules are the delta between 'lab demo' and 'deployable'. |

## 4.2 Prioritized Roadmap

| # | Initiative | Objective Alignment | Owner | Timeline | Dependencies | Success Criteria |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Rotate hardcoded LDAP token; enable LDAPS (AUTHENTIK_INSECURE=false) | Production rigor; auditable evidence | DevSecOps Engineer | Days 1–3 | Vault available | Token unique per environment; TLS verified on 636 |
| 2 | Enforce MFA + lockout in Authentik | IAM skills; lab operability | IAM Engineer | Weeks 1–2 | — | 100% human users enrolled; lockout tested |
| 3 | Vault token hygiene (revoke root; TTLs) | Production rigor | DevSecOps Engineer | Week 1 | — | No root token in use; audit log clean |
| 4 | Wazuh detection rules (6 mandatory) + simulated-event testing | Auditable evidence; detection | Security Analyst | Month 1 | Wazuh deployed | All 6 rules fire on synthetic events |
| 5 | git-secrets + Trufflehog in workflow | Prevent recurrence | DevSecOps Engineer | Week 2 | — | Clean scan of history; hook blocks test commit |
| 6 | Worker non-root; scope docker.sock; remove whoami from prod profile | Attack-surface reduction | IAM Engineer | Month 2 | Regression test | Compose diff reviewed; services healthy |
| 7 | Quarterly access recertification process live | Sustained least privilege | IAM Engineer | Month 2–3 | — | First recertification signed off |
| 8 | Number matching + push rate limits + user training | MFA resilience | IAM Engineer | Month 2 | MFA enforced (2) | Training delivered; 0 blind approvals in test |
| 9 | Cyber-insurance evaluation | Financial transfer | System Owner | Month 2–3 | Controls 1–4 complete | Quote obtained; decision recorded |
| 10 | Formalize risk acceptances; integrate register into monthly reviews | Governance | System Owner | Month 3 | — | Signed acceptances filed; review cadence in calendar |

## 4.3 Quick Wins vs. Strategic Initiatives

Quick wins (0–30 days) — high impact, minimal effort:

- Rotate the hardcoded AUTHENTIK_TOKEN and move it to Vault (closes the single most embarrassing finding).

- Enforce MFA and account lockout in Authentik (biggest single reduction in credential-theft risk).

- Revoke the Vault root token and set AppRole TTLs.

- Remove whoami from the production compose profile.

Strategic initiatives (1–6 months) — structural improvements:

- Full Wazuh detection program with tested rules and monthly coverage reviews.

- Quarterly access recertification as a repeatable, evidenced process.

- Container hardening (non-root worker, scoped docker socket).

- Cyber-insurance decision and formal risk-acceptance governance.

# 5. Residual Risk Calculation

## 5.1 Scoring Method

Likelihood × Impact on a 5-point scale (1=Rare … 5=Almost Certain; 1=Negligible … 5=Catastrophic). Score 1–4 Low, 5–9 Medium, 10–14 High, 15–25 Critical — consistent with EISP-RR-003's qualitative ratings.

| Risk ID | Risk | Inherent (L×I) | Inherent Level | Applied Controls | Residual (L×I) | Residual Level |
| --- | --- | --- | --- | --- | --- | --- |
| RR-001 | Credential Theft | 4×5=20 | CRITICAL | MFA enforced (PR.AC-07/A.8.5); lockout; impossible-travel + failed-login detection (DE.CM-01/A.8.16); daily log review | 2×5=10 | MEDIUM |
| RR-002 | Privilege Escalation | 4×5=20 | CRITICAL | Permission boundary on all roles (PR.AC-04/A.5.18); Wazuh self-modification alert; JIT 4h STS sessions; quarterly recertification | 2×5=10 | MEDIUM |
| RR-003 | Secrets Exposure | 3×4=12 | HIGH | Token rotated to Vault; LDAPS enforced; git-secrets + Trufflehog (PR.DS-01, PR.PS-01 / A.8.9) | 1×4=4 | LOW |
| RR-004 | MFA Fatigue | 3×4=12 | HIGH | Number matching; 3-push/5-min rate limit; Wazuh spike detection; user training (PR.AC-07 / A.8.5, A.6.3) | 2×4=8 | MEDIUM |
| RR-005 | Vault Token Compromise | 2×5=10 | HIGH | Root token revoked; AppRole TTL 24h + use-limit 5; weekly audit-log review (PR.DS-01 / A.5.17, A.8.15) | 1×5=5 | MEDIUM |
| RR-010 | Detection Rule Gaps | 3×4=12 | HIGH | 6 mandatory Wazuh rules implemented and tested; monthly coverage review (DE.CM / A.8.16) | 2×4=8 | MEDIUM |

Result: both CRITICAL inherent risks are reduced to MEDIUM; no risk remains above MEDIUM after the plan. Impact stays high for identity risks (a compromised IdP is inherently severe) — mitigation buys this down through likelihood reduction, which is the correct lever when impact is structural.

## 5.2 Control Effectiveness Measurements

Each control's effectiveness is measured, not assumed:

| Metric | Target | Measurement Method | Frequency |
| --- | --- | --- | --- |
| MFA enrollment rate (human users) | 100% | Authentik user report: users with MFA device / total active users | Weekly |
| Mean time to rotate credentials after suspected compromise | < 4 hours | Incident tickets: detection timestamp → rotation confirmation | Per incident |
| % of AWS roles carrying the permission boundary | 100% | Terraform plan + AWS IAM API audit | Monthly |
| Access recertifications completed on time | 100% quarterly | Signed recertification records vs. schedule | Quarterly |
| Secrets-scan findings in repo | 0 | Trufflehog full-history scan findings count | Monthly |
| Wazuh mandatory rules firing on synthetic tests | 6/6 | Quarterly simulated-event test results | Quarterly |
| MFA push-approval anomalies (blind approvals) | 0 | Wazuh MFA-spike alerts + user reports | Weekly |
| Overdue risk-review items | 0 | Risk register review dates vs. scheduled frequency | Monthly |

## 5.3 Monitoring Procedures

Aligned to the Monitoring SOP sheet of EISP-RR-003 — what is watched, how often, by whom, and what triggers escalation:

| What Is Monitored | How Often | By Whom | Alert Threshold | Escalation |
| --- | --- | --- | --- | --- |
| Authentik sign-in logs (failed logins, MFA anomalies) | Weekly (Monday) | IAM Engineer | >5 failed MFA attempts for one user, or any impossible-travel alert | IAM Engineer → Security Lead |
| AWS CloudTrail: AttachRolePolicy / CreateRole events | Weekly | IAM Engineer | Any role-policy change not in the change log | IAM Engineer → Security Lead |
| Vault audit log (secret path access, token use) | Weekly | DevSecOps Engineer | Root token usage, or unusual secret-path access | DevSecOps → Security Lead (immediate) |
| Repository secret scan (Trufflehog) | Monthly | DevSecOps Engineer | Any credential found | Immediate rotation; IAM Engineer notified |
| Wazuh rule health + coverage review | Monthly | Security Analyst | Rule silent >30 days, or new ATT&CK technique uncovered | Security Analyst → IAM Engineer |
| Risk register review cycle | Per risk frequency (weekly/monthly) | Risk owners | Overdue review or new risk identified | Owner → System Owner |
| Docker host resource utilization | Per deployment | DevSecOps Engineer | RAM > 90% | Reduce workload or move to VM |

Monitoring outputs feed back into Section 5.2 metrics; any metric missing its target for two consecutive cycles re-opens the corresponding risk for re-treatment.

# 6. Conclusion

This plan converts the EISP Risk Register from a list of worries into an executable program: 18 framework controls selected with explicit rationale, all four treatment strategies applied with EISP-specific examples, a 10-initiative roadmap sequenced over six months, and residual risk quantified for every top risk — with no risk left above MEDIUM. Because the highest-priority mitigations are configuration changes in systems already deployed (Authentik, Terraform, Wazuh, Vault), the plan is achievable within a lab team's effort budget while demonstrating the exact control-selection, treatment-decision, and residual-risk discipline expected of an IAM engineer operating under NIST CSF 2.0 and ISO/IEC 27001:2022.

Next steps: execute the Day 1–3 quick wins (token rotation, MFA enforcement, Vault hygiene), stand up the weekly monitoring cadence, and file the first signed risk acceptance — momentum in the first two weeks determines whether the six-month roadmap holds.