## Risk Register
EISP — Risk Register ¦ EISP-RR-003 ¦ Version 1.0 ¦ April 2026 ¦ Author: Manisha Gupta ¦ CONFIDENTIAL
Risk ID | Category | Risk Description | Likelihood | Impact | Risk Rating | CVSS Score | MITRE Technique | Treatment | Mitigation Steps | Owner | Review Frequency | Status
RR-001 | Credential Theft | Attacker steals authentik or AWS IAM credentials via phishing or brute force, gaining unauthorized access to EISP environment | High | Critical | CRITICAL | 9.8 | T1566 / T1110 | Mitigate | 1. Enforce MFA for all accounts via authentik flow 2. Enable impossible travel detection rule in Wazuh 3. Set account lockout after 5 failed attempts 4. Rotate all credentials immediately on suspected compromise 5. Review sign-in logs daily | IAM Engineer | Weekly | Open
RR-002 | Privilege Escalation | Compromised standard user account attempts to escalate privileges by modifying IAM role policies or assuming higher-privilege roles | High | Critical | CRITICAL | 9.1 | T1548 / T1078 | Mitigate | 1. Enforce IAM permission boundaries on all roles 2. Enable Wazuh detection rule for self-policy modification 3. Implement JIT access for privileged roles (max 4h) 4. Review CloudTrail for AttachRolePolicy events daily 5. Quarterly access re-certification | IAM Engineer | Weekly | Open
RR-003 | Secrets Exposure — Hardcoded Credentials | Developer accidentally commits API key or Vault token to Git repository, exposing credentials publicly or to team members | Medium | High | HIGH | 8.2 | T1552 | Mitigate | 1. Install git-secrets pre-commit hook on all repos 2. Run Trufflehog scan on existing repository history 3. Store all secrets in HashiCorp Vault — never in code 4. Use .gitignore to exclude .env files 5. Immediate rotation if any hardcoded credential is found | DevSecOps Engineer | Monthly | Open
RR-004 | MFA Fatigue Attack | Attacker obtains user password and floods the user with MFA push notifications until the user approves out of frustration | Medium | High | HIGH | 7.5 | T1621 | Mitigate | 1. Enable number matching on all push MFA (prevents blind approval) 2. Set push notification rate limit: max 3 per 5 minutes 3. Configure Wazuh MFA spike detection rule (5+ failures in 10 min) 4. Educate users: never approve unexpected MFA requests 5. Offer FIDO2 passkey as stronger alternative | IAM Engineer | Monthly | Open
RR-005 | Vault Token Compromise | Vault root token or AppRole secret_id is exposed or stolen, giving attacker full access to all secrets stored in Vault | Low | Critical | HIGH | 8.8 | T1552 / T1078 | Mitigate | 1. Revoke root token immediately after initial setup — use admin policy token 2. Set AppRole secret_id TTL to 24h and use_limit to 5 3. Enable Vault audit logging and monitor for unusual path access 4. Store root token recovery shards in separate secure locations 5. Create Wazuh rule for Vault path access outside normal scope | DevSecOps Engineer | Weekly | Open
RR-006 | OpenCTI Docker Resource Exhaustion | OpenCTI Docker stack (ElasticSearch/OpenSearch) consumes excessive RAM on MacBook M4 causing system instability | Medium | Medium | MEDIUM | 4.0 | N/A — Infrastructure | Accept/Mitigate | 1. Allocate minimum 8GB RAM to Docker Desktop 2. Set JVM heap limits: -Xms512m -Xmx1g for OpenSearch 3. Deploy OpenCTI on a dedicated VM if RAM is insufficient 4. Use lightweight connector set — MITRE ATT&CK only initially 5. Monitor Docker stats: docker stats during deployment | DevSecOps Engineer | Per deployment | Open
RR-007 | ARM64 Tool Incompatibility | A required security tool (Kali package, Docker image) does not support ARM64 architecture of MacBook Air M4, blocking task completion | Medium | Medium | MEDIUM | 5.0 | N/A — Infrastructure | Mitigate | 1. Pre-validate ARM64 support for all Docker images before deployment 2. Use UTM (free) as hypervisor fallback for x86_64 VMs via emulation 3. Replace incompatible tools with ARM64-compatible alternatives 4. Use cloud-based sandboxes (Any.Run) for tools requiring x86 5. Document any substitutions in project notes | IAM Engineer | Per tool addition | Open
RR-008 | AWS Free Tier Limit Exceeded | Exceeding AWS Free Tier usage limits results in unexpected charges, potentially requiring project shutdown of cloud resources | Low | Medium | MEDIUM | 3.0 | N/A — Cost | Mitigate | 1. Set AWS Billing Alert at $5 threshold via CloudWatch 2. Use t2.micro or t3.micro instances only 3. Terminate EC2 instances when not in use (stop, not just stop) 4. Monitor S3 CloudTrail storage — implement lifecycle policy 5. Use free tier calculator before launching new services | IAM Engineer | Weekly | Open
RR-009 | Phishing Simulation Escapes Lab Scope | SET phishing template or credential harvester accidentally accessible outside the controlled lab environment | Low | High | MEDIUM | 6.5 | T1566 — risk of misuse | Mitigate | 1. Run SET only on isolated local network (host-only adapter in VirtualBox) 2. Disable external network access on Kali VM during phishing simulation 3. Immediately shut down SET after task completion 4. Document in lab notes that all phishing activity is controlled simulation 5. Never use real email addresses or production systems as targets | Security Analyst | Per task | Open
RR-010 | Wazuh Detection Rule Gaps | Critical attack scenarios are not covered by detection rules, allowing attacker activity to go undetected in the SIEM | Medium | High | HIGH | 7.0 | T1562.001 | Mitigate | 1. Implement all 6 mandatory detection rules before Week 4 end 2. Test each rule with a simulated event before marking complete 3. Review Wazuh rule coverage quarterly against MITRE ATT&CK matrix 4. Add new rules when new attack techniques are identified 5. Monitor Wazuh rule firing rate — suppressed rules must be investigated | Security Analyst | Monthly | Open

## Risk Summary
EISP Risk Summary Dashboard ¦ EISP-RR-003
Risk Distribution by Rating
CRITICAL | 2
HIGH | 4
MEDIUM | 3
LOW | 0
Risk Heat Map (Likelihood vs Impact)
| Low Impact | Medium Impact | High Impact | Critical Impact
High Likelihood |  | RR-006 | RR-004, RR-010 | RR-001, RR-002
Medium Likelihood |  | RR-007, RR-008 |  | RR-003
Low Likelihood |  |  | RR-009 | RR-005

## Monitoring SOP
EISP Risk Monitoring Procedure ¦ Standard Operating Procedure
Risk ID | Review Trigger | Review Steps | Escalation Condition | Escalate To
RR-001 | Weekly — Monday morning log review | 1. Pull authentik sign-in logs for past 7 days 2. Check Wazuh for MFA spike / impossible travel alerts 3. Verify no new admin accounts created without approval 4. Confirm CloudTrail shows no unexpected AssumeRole events | Any failed MFA spike >5 attempts OR impossible travel alert fired | IAM Engineer → Security Lead
RR-002 | Weekly — CloudTrail review | 1. Query CloudTrail for AttachRolePolicy and CreateRole events 2. Verify no roles modified outside approved workflow 3. Check Wazuh privilege escalation rule for alerts 4. Confirm JIT access grants have expired as configured | Any role policy modification not in change log | IAM Engineer → Security Lead
RR-003 | Monthly — Code repository scan | 1. Run Trufflehog against all EISP Git repositories 2. Review .gitignore for .env and credential files 3. Verify all Vault AppRole secret_ids were issued, not hardcoded 4. Confirm pre-commit hooks active on all developer machines | Any credential found in repository | DevSecOps → IAM Engineer (immediate rotation)
RR-005 | Weekly — Vault audit log review | 1. Review Vault audit log for access to sensitive paths 2. Verify AppRole tokens have not exceeded normal TTL 3. Check for any root token usage (should be zero after setup) 4. Confirm audit device is running and log file is updating | Root token usage detected OR unusual secret path access | DevSecOps → Security Lead (immediate)
RR-006 | Per deployment — Resource check | 1. Run docker stats before and during OpenCTI startup 2. Verify Docker Desktop RAM allocation is >= 8GB 3. Monitor MacBook Activity Monitor during deployment 4. Set JVM heap limits before first connector run | System RAM > 90% utilization | DevSecOps — reduce connector set or move to VM